## SYSTEM INTEGRATION 2
SYSTEM INTEGRATION AND ARCHITECTURE 2
PROJECT TITLE |  |  | START DATE
GOTRANSPO: A USER-CENTRIC BUS RESERVATION SYSTEM FOR CONVENIENT AND INCLUSIVE TRAVEL |  |  | 2025-02-01 |  |  | PROJECT DURATION
TEACHER |  |  | END DATE |  |  | in days
Sir John Rentie V. Diaz |  |  | 2025-05-30 |  |  | 118
WBS NO. | TASK NAME | STATUS | ASSIGNED TO | START DATE | END DATE | DURATION in days | MY COMMENTS | PROF/JERIC'S COMMENTS
1 | INTRODUCTION | In Progress | ALL | 2024-02-07 |  | -45329
1.1 | PPT for Development Methodology | Complete | Jeric | 2024-02-07 | 2024-02-08 | 1 | Uploaded
1.1.1 | Development Methodology Class Presentation | Complete | All | 2025-02-10 | 2025-02-10 | 0 |  | 95%
1.2 | Letter for Company | Complete | All | 2025-02-11 | 2025-02-11 | 0 | Uploaded; Revision uploaded;Second revision uploaded
1.2.1 | Interview with the Company | Complete | All | 2025-02-11 | 2025-02-11 | 0 |  | Keep: Juliet
1.2.2 | PPT for Process Activities | Complete | Jeric | 2025-02-11 | 2025-02-17 | 6 | Uploaded
1.2.3 | Process Activities Presentation | Complete | All | 2025-02-11 | 2025-02-17 | 6 |  | 99%
1.3 | PPT for Prototype | Complete | Jeric | 2025-02-19 | 2025-02-24 | 5
1.3.1 | Prototype Presentation | Complete | All | 2025-02-19 | 2025-02-24 | 5 |  | 98%

## CAPSTONE 1
CAPSTONE 1
PROJECT TITLE |  |  | START DATE
|  |  | 2025-02-05 |  |  | PROJECT DURATION
TEACHER |  |  | END DATE |  |  | in days
Ma'am Zerah-jane M. Astoveza |  |  | 2025-05-30 |  |  | 114
WBS NO. | TASK NAME | STATUS | ASSIGNED TO | START DATE | END DATE | DURATION in days | MY COMMENTS | PROF/JERIC'S COMMENTS
1 | INTRODUCTION | In Progress | ALL | 2025-02-07 |  | -45695
1.1 | 17 Sustainable Development Goals & AI Tools | Complete | Jeric | 2025-02-05 | 2025-02-12 | 7 | Uploaded
1.2 | 17 Sustainable Development Goals & AI Tools | Complete | Juliet | 2025-02-05 | 2025-02-12 | 7 | Uploaded | no AI Tools
1,3 | 17 Sustainable Development Goals & AI Tools | Complete | Honeylyn | 2025-02-05 | 2025-02-12 | 7 | Uploaded | no AI Tools
1.4 | 3 Initial Titles with 15 RRL | In Progress | Jeric | 2025-02-05 | 2025-02-12 | 7 | As of now: 1 title with 15 RRL
1.5 | 3 Initial Titles with 15 RRL | In Progress | Juliet | 2025-02-05 | 2025-02-12 | 7 | As of now: 1 title with 20 RRl
1.6 | 3 Initial Titles with 15 RRL | In Progress | Honeylyn | 2025-02-05 | 2025-02-12 | 7
1.2 | AI Tools Video | Complete | All | 2025-02-19 | 2025-02-19 | 0 | Uploaded

## SCHEDULE
DROPDOWN KEYS - Do Not Delete
STATUS
Not Started
In Progress
Complete
On Hold